TWNG Migration Plan

Our Frontend + Lovable Backend

Two Options: Claude API vs. Gemini API

February 2026

# Table of Contents

Table of Contents	1

1. Current State Overview	1

1.1 What We Have (Claude Build)	1

1.2 What Lovable Has	1

1.3 Target Architecture (per Architecture Skill)	1

1.4 Goal	1

2. Shared Steps (Both Options)	1

Step 1: Database Migration	1

Step 2: Deploy Edge Functions	1

Step 3: Frontend Data Layer Rewrite	1

Step 4: Auth Alignment	1

3. Option A: Keep Claude API	1

3.1 Edge Functions to Deploy	1

3.2 Additional Claude-Only Assets to Migrate	1

3.3 Work Estimate — Option A	1

3.4 Pros & Cons — Option A	1

4. Option B: Switch to Gemini API	1

4.1 Edge Functions to Deploy	1

4.2 Assets to Migrate	1

4.3 Work Estimate — Option B	1

4.4 Pros & Cons — Option B	1

5. Feature Gap: Frontend Pages to Build	1

5.1 Summary	1

6. Shared Components to Build	1

7. Recommended Implementation Phases	1

Phase 1: Foundation (Week 1–2)	1

Phase 2: Social Layer (Week 2–3)	1

Phase 3: Content (Week 3–4)	1

Phase 4: Polish (Week 4–5)	1

8. Decision Matrix	1

# 1. Current State Overview

## 1.1 What We Have (Claude Build)

Frontend: Vite 7 + React 19 + React Router 7 + JavaScript (no TypeScript). Deployed on Netlify.

Backend: Supabase with 22+ tables, 6 Edge Functions (Anthropic Claude API), 15 service files in src/lib/. Supabase project ref: iqrmwetprpwjgzynrjay.

Unique assets: Guitar catalog (419 pre-loaded models), serial number decoder, 2-phase AI content extraction pipeline, multi-provider email (Resend + SendGrid + Mailgun), ownership transfer system, KPI dashboard.

## 1.2 What Lovable Has

Frontend: Vite + React + TypeScript + React Query. 36 routes, 45+ UI components, 46 hooks.

Backend: Supabase with 18+ tables, 109 migrations, 50+ RLS policies, 8 Edge Functions (Google Gemini 2.5 Flash + remove.bg), realtime on 3+ tables.

Unique assets: Full social layer (forum, follows, blocks, badges, activity feed, favorites), advanced search (20+ filters), database backup/restore, role-based access, homepage customization blocks, instrument archive/restore, duplicate detection.

## 1.3 Target Architecture (per Architecture Skill)

The decided stack (Feb 2026) specifies Next.js + TypeScript + shadcn/ui + Vercel. Neither the current Claude build (Vite/JS) nor the Lovable build (Vite/TS) matches this target. The migration plan assumes staying on Vite + React for now, with the option to migrate to Next.js as a separate future project.

## 1.4 Goal

Keep our frontend (UI/UX, design system, component library) and connect it to Lovable's backend (database schema, RLS policies, Edge Functions, realtime) as the production backend. Lovable's feature set becomes the functional baseline — our frontend must eventually support all features that exist in Lovable.

# 2. Shared Steps (Both Options)

These steps are identical regardless of which AI provider you choose.

## Step 1: Database Migration

Goal: Get Lovable's full database schema running on our Supabase project (or a new one).

- Option A: Fresh Supabase project — run all 109 Lovable migrations in order on a clean project. Safest, no conflicts. Loses our existing data (can be migrated separately).

- Option B: Merge into existing project — manually apply Lovable's schema changes to our Supabase instance. Complex, requires resolving naming conflicts (guitars vs instruments, different user schemas).

- Recommendation: Fresh project. Our current data is mostly test data. A clean start is faster and safer.

Deliverables:

- All Lovable tables created (instruments, collections, forum_categories, forum_threads, forum_posts, user_follows, user_blocks, user_badges, user_activity, articles, article_tags, etc.)

- All 50+ RLS policies applied

- All indexes and constraints in place

- is_blocked() cascading function deployed

- Realtime enabled on: notifications, messages, user_follows

- Storage buckets: article-images, instrument-images

- Estimated time: 2–4 hours (fresh) / 1–2 days (merge)

## Step 2: Deploy Edge Functions

Deploy the Edge Functions appropriate for your chosen AI option (see Option A / Option B below).

## Step 3: Frontend Data Layer Rewrite

This is the biggest piece of work. Our frontend talks to Supabase through 15 service files in src/lib/. These must be rewritten to match Lovable's schema.

Key mapping changes:

| Area | Our Schema | Lovable Schema | Frontend Impact |
| --- | --- | --- | --- |
| Table name | guitars | instruments | All queries, types, components |
| User columns | nickname, avatar | username, avatar_url, first_name, last_name | Profile display, auth context |
| Specs storage | 30+ explicit columns | JSONB specification fields | All spec display/edit forms |
| Sale info | is_for_sale, price columns | sale_info JSONB | Sale/marketplace views |
| Content | owner_created_content | articles + article_tags + article_collections | Content creation/display |
| Forum | Not present | forum_categories, forum_threads, forum_posts | New pages needed |
| Social graph | Not present | user_follows, user_blocks | New components needed |
| Search | Basic text match | 20+ filter fields on instruments | Search UI rewrite |
| Auth/roles | Basic auth | useRole hook, role-based guards | Route protection logic |

Approach:

- Create a new src/lib/supabase/ directory with typed client functions matching Lovable's schema

- Replace all direct Supabase queries in components with calls to these new functions

- Add React Query (TanStack) for caching and state management — this is highly recommended and matches both Lovable's pattern and industry best practice

- Estimated time: 3–5 days for core CRUD, 1–2 weeks for full feature parity

## Step 4: Auth Alignment

Both builds use Supabase Auth. Key differences to resolve:

- Our auth context uses a simple useState pattern. Lovable uses React Query for auth state. Either works, but React Query is cleaner with the rest of the data layer.

- Lovable has useRole() hook for role-based access (admin, moderator, etc.). We need to add route guards matching their pattern.

- User profile schema differs: add first_name, last_name, privacy_settings, bio fields to our profile edit form.

- Estimated time: 0.5–1 day

# 3. Option A: Keep Claude API

Use Lovable's DB schema + RLS + social features. Replace Lovable's AI Edge Functions with our Claude-powered ones. Keep our unique assets (catalog, serial decoder, extraction pipeline).

## 3.1 Edge Functions to Deploy

| Function | Action | Status | Notes |
| --- | --- | --- | --- |
| extract-content | Keep (ours) | ✅ Deploy as-is | 2-phase AI extraction pipeline. Proxy mode for frontend Claude calls. |
| extract-post | Keep (ours) | ✅ Deploy as-is | Social media post extraction. |
| analyze-guitar | Keep (ours) | ✅ Deploy as-is | AI analysis from images/text. |
| verify-guitar | Keep (ours) | ✅ Deploy as-is | Serial verification + specs lookup. |
| transcribe-audio | Keep (ours) | ✅ Deploy as-is | Audio transcription capability. |
| send-email | Keep (ours) | ✅ Deploy as-is | Multi-provider email (3 providers, 3 templates). |
| magic-add-identify | Rewrite | ⚠️ Rewrite to use Claude | Replace Gemini 2.5 Flash with Claude API. Same input/output contract. |
| generate-instrument-specs | Rewrite | ⚠️ Rewrite to use Claude | Replace Gemini with Claude for spec generation. |
| guitar-price-evaluation | Rewrite | ⚠️ Rewrite to use Claude | Replace Gemini with Claude for price evaluation. |
| remove-background | Keep (Lovable) | ✅ Deploy as-is | Uses remove.bg API, not AI-provider-dependent. |
| create-backup | Keep (Lovable) | ✅ Deploy as-is | Database backup. No AI dependency. |
| restore-backup | Keep (Lovable) | ✅ Deploy as-is | Database restore. No AI dependency. |
| send-contact-email | Merge | ⚠️ Merge into send-email | Consolidate with our multi-provider send-email. |
| submit-identification-feedback | Keep (Lovable) | ✅ Deploy as-is | User feedback loop. No AI dependency. |

## 3.2 Additional Claude-Only Assets to Migrate

- guitar_catalog table: Create migration to add this table to Lovable's schema. Load 419 models. Powers our autocomplete.

- seed_guitars table: Create migration. Required by extract-content pipeline output.

- serialDecoder.js: Keep in frontend src/lib/. No backend dependency.

- kpiService.js: Keep and adapt queries to new table names (instruments instead of guitars).

- emailService.js: Keep. Works with our send-email Edge Function.

## 3.3 Work Estimate — Option A

| Task | Time | Risk | Notes |
| --- | --- | --- | --- |
| Fresh Supabase project + run 109 migrations | 2–4 hours | Low | Straightforward |
| Add guitar_catalog + seed_guitars migrations | 2–4 hours | Low | New tables for our assets |
| Rewrite 3 Gemini Edge Functions to Claude | 1–2 days | Medium | Same contracts, different API |
| Deploy all 14 Edge Functions | 0.5 day | Low | CLI deployment |
| Frontend data layer rewrite (src/lib/) | 3–5 days | High | Biggest task |
| Auth + role alignment | 0.5–1 day | Medium | useRole, route guards |
| Feature gap: new pages + components | 5–10 days | High | Forum, follows, blocks, etc. |
| Testing + bug fixes | 2–3 days | Medium | Integration testing |
| TOTAL | 2–4 weeks |  |  |

## 3.4 Pros & Cons — Option A

Pros:

- Keep all our unique AI capabilities (extraction pipeline, analysis, verification, transcription)

- Keep guitar catalog (419 models) — significant data asset

- Keep multi-provider email infrastructure

- Claude API is generally stronger for complex structured extraction tasks

- No vendor dependency on Google for core AI features

Cons:

- Must rewrite 3 Edge Functions (Gemini → Claude) — extra work

- Claude API is more expensive per token than Gemini 2.5 Flash

- Must maintain ANTHROPIC_API_KEY as a dependency

- 2 additional DB migrations needed (catalog + seed tables)

# 4. Option B: Switch to Gemini API

Adopt Lovable's backend as-is, including all 8 Gemini-based Edge Functions. Migrate our unique non-AI assets (catalog, email) but drop the Claude-specific extraction pipeline.

## 4.1 Edge Functions to Deploy

| Function | Action | Status | Notes |
| --- | --- | --- | --- |
| magic-add-identify | Keep (Lovable) | ✅ Deploy as-is | Gemini 2.5 Flash guitar identification. |
| generate-instrument-specs | Keep (Lovable) | ✅ Deploy as-is | Gemini spec generation. |
| guitar-price-evaluation | Keep (Lovable) | ✅ Deploy as-is | Gemini price evaluation. |
| remove-background | Keep (Lovable) | ✅ Deploy as-is | remove.bg API. |
| create-backup | Keep (Lovable) | ✅ Deploy as-is | Database backup. |
| restore-backup | Keep (Lovable) | ✅ Deploy as-is | Database restore. |
| send-contact-email | Keep (Lovable) | ✅ Deploy as-is | Resend contact email. |
| submit-identification-feedback | Keep (Lovable) | ✅ Deploy as-is | Feedback loop. |
| send-email (ours) | Adapt | ⚠️ Adapt to new schema | Keep multi-provider email but update table references. |
| verify-guitar (ours) | Rewrite | ⚠️ Rewrite for Gemini | Serial verification — needs catalog table. |
| extract-content (ours) | DROP | ❌ Not migrated | 2-phase pipeline is Claude-specific. Replace with magic-add-identify. |
| extract-post (ours) | DROP | ❌ Not migrated | Functionality partially covered by magic-add-identify. |
| analyze-guitar (ours) | DROP | ❌ Not migrated | Functionality covered by generate-instrument-specs. |
| transcribe-audio (ours) | DROP or Rewrite | ⚠️ Optional: rewrite for Gemini | Audio transcription not critical for MVP. |

## 4.2 Assets to Migrate

- guitar_catalog table: Still add this migration — 419 models are valuable regardless of AI provider.

- serialDecoder.js: Keep in frontend. Purely regex, no AI dependency.

- emailService.js: Keep and adapt to new schema (table names).

- kpiService.js: Keep and adapt.

- DROP: ContentExtractor.jsx, seed_guitars table, extract-content pipeline.

## 4.3 Work Estimate — Option B

| Task | Time | Risk | Notes |
| --- | --- | --- | --- |
| Fresh Supabase project + run 109 migrations | 2–4 hours | Low | Straightforward |
| Add guitar_catalog migration | 1–2 hours | Low | One new table |
| Deploy 8 Lovable Edge Functions + adapted send-email | 0.5 day | Low | CLI deployment |
| Set up Gemini API key + remove.bg key | 1 hour | Low | Secrets configuration |
| Frontend data layer rewrite (src/lib/) | 3–5 days | High | Biggest task |
| Remove Claude-specific components (ContentExtractor) | 0.5 day | Low | Cleanup |
| Auth + role alignment | 0.5–1 day | Medium | useRole, route guards |
| Feature gap: new pages + components | 5–10 days | High | Forum, follows, blocks, etc. |
| Testing + bug fixes | 2–3 days | Medium | Integration testing |
| TOTAL | 2–3.5 weeks |  |  |

## 4.4 Pros & Cons — Option B

Pros:

- Fastest path — deploy Lovable's backend as-is with minimal rewrites

- Gemini 2.5 Flash is significantly cheaper per token than Claude

- Already tested and working in Lovable's production environment

- Less Edge Function code to maintain (8 vs 14)

- Simpler: one AI provider instead of managing Claude + Gemini

Cons:

- Lose the 2-phase extraction pipeline (our most sophisticated AI feature)

- Gemini is less reliable for complex structured extraction than Claude

- Lose audio transcription (unless rewritten for Gemini)

- Lose seed_guitars auto-population workflow

- Vendor dependency on Google for all AI features

# 5. Feature Gap: Frontend Pages to Build

Using Lovable's 36 routes as the functional baseline, the following maps what we have, what's missing, and what needs to be built. This section applies to BOTH options.

| Route | Page | Our Status | Work Required |
| --- | --- | --- | --- |
| / | Home | ✅ Exists | Redesign with NewArrivals, FeaturedBlog, CTA, PresenceIndicator sections |
| /auth | Auth | ✅ Exists | Minor: add role-based redirect, first_name/last_name fields |
| /upload | Add Instrument | ✅ Exists (AddGuitar) | Rename, adapt form fields to 'instruments' schema, integrate magic-add |
| /explore | Explore/Browse | ✅ Exists (Browse) | Major rewrite: add 20+ filter sidebar, card redesign |
| /guitar/:id | Instrument Detail | ✅ Exists | Adapt to instruments schema, add tabs for specs/timeline/comments |
| /guitar/:id/edit | Edit Instrument | ✅ Exists | Adapt form to instruments schema |
| /admin | Admin Dashboard | ✅ Exists (partial) | Expand with user management, content moderation, system settings |
| /profile | My Profile | ✅ Exists | Add: badges display, activity feed, follows count, bio |
| /profile/edit | Edit Profile | ✅ Exists | Add: first_name, last_name, privacy_settings, bio fields |
| /user/:userId | Public Profile | ⚠️ Basic | Add: follow/block buttons, badges, public instruments, activity |
| /my-instruments | My Instruments | ⚠️ Basic | Add: archive/restore, duplicate check, better grid/list toggle |
| /collections | Collections | ❌ Missing | NEW: collection browsing, featured collections |
| /collections/new | Create Collection | ❌ Missing | NEW: form with cover image, description, instrument picker |
| /collections/:id | Collection Detail | ❌ Missing | NEW: instrument grid, owner info, favorite button |
| /collections/:id/edit | Edit Collection | ❌ Missing | NEW: edit form, manage items |
| /my-collections | My Collections | ❌ Missing | NEW: user's own collections list |
| /my-favorites | My Favorites | ❌ Missing | NEW: favorited instruments and collections |
| /messages | Messages | ❌ Missing | NEW: conversation list, message thread, send/receive, realtime |
| /forum | Forum Home | ❌ Missing | NEW: category list, pinned threads, recent activity |
| /forum/category/:slug | Forum Category | ❌ Missing | NEW: thread list, create thread button, search |
| /forum/new | New Thread | ❌ Missing | NEW: thread creation form |
| /forum/thread/:id | Thread Detail | ❌ Missing | NEW: replies, reply form, mark as solution, pin/lock |
| /articles | Articles | ❌ Missing | NEW: article listing, tags, search |
| /articles/:slug | Article Detail | ❌ Missing | NEW: article content, tags, comments, related articles |
| /tags | Tags | ❌ Missing | NEW: tag cloud/list, instruments per tag |
| /about | About | ❌ Missing | NEW: static page |
| /faq | FAQ | ❌ Missing | NEW: static page |
| /terms | Terms | ❌ Missing | NEW: static page |
| /vision | Vision | ❌ Missing | NEW: static page |
| /guidelines | Guidelines | ❌ Missing | NEW: static page |
| /contact | Contact | ❌ Missing | NEW: contact form, uses send-contact-email Edge Function |
| /test/price-evaluator | Price Evaluator | ❌ Missing | NEW: AI price evaluation tool page |
| /test/background-removal | BG Removal | ❌ Missing | NEW: image upload + background removal tool page |

## 5.1 Summary

Existing pages that need adaptation: 11 (green/yellow). Completely new pages to build: 22 (red). Total routes in Lovable: 33 (excluding test pages). Our frontend covers roughly one-third of Lovable's route map. The biggest gaps are: Collections (5 pages), Forum (4 pages), Articles (2 pages), Messages (1 page), and static/info pages (5 pages).

# 6. Shared Components to Build

Beyond pages, these reusable components need to be created or adapted in our frontend:

| Component | Purpose | Backend Dependency | Priority |
| --- | --- | --- | --- |
| FollowButton | Follow/unfollow user toggle | useUserFollows hook | High |
| BlockButton | Block/mute user | useUserBlocks hook | High |
| FavoriteButton | Favorite instrument/collection | useFavorites hook | High |
| BadgeDisplay | Show user badges on profile | useUserBadges hook | Medium |
| ActivityFeed | Activity timeline widget | useActivityFeed hook | Medium |
| NotificationDropdown | Header notification bell | useNotifications + realtime | High |
| MessageDropdown | Header message indicator | useMessaging + realtime | High |
| GlobalSearchBar | Cross-entity search | useGlobalSearch hook | High |
| AdvancedSearchSidebar | 20+ filter panel | useAdvancedSearch hook | High |
| ForumThread | Thread display with replies | useForum hook | Medium |
| ArticleCard | Article preview card | useArticles hook | Medium |
| CollectionCard | Collection preview card | useCollections hook | Medium |
| ImageWithBgRemoval | Image upload + BG removal | remove-background Edge Fn | Low |
| PriceEvaluator | AI price evaluation form | guitar-price-evaluation Edge Fn | Low |
| RoleGuard | Route access by role | useRole hook | High |
| ThemeToggle | Dark/light mode switch | CSS variables / context | Low |

# 7. Recommended Implementation Phases

## Phase 1: Foundation (Week 1–2)

Get the backend running and core pages working.

- Set up fresh Supabase project, run all migrations

- Deploy Edge Functions (per chosen option)

- Rewrite src/lib/ data layer for instruments schema

- Adapt auth context + add useRole

- Get existing pages working: Home, Auth, Add Instrument, Browse, Detail, Edit, Profile

- Add React Query for data fetching

## Phase 2: Social Layer (Week 2–3)

Add the social features that make TWNG a community, not just a catalog.

- Build Messages page (realtime)

- Build Notifications dropdown (realtime)

- Add FollowButton, BlockButton, FavoriteButton components

- Build Public Profile page with follows/badges/activity

- Build My Favorites page

- Add GlobalSearchBar + AdvancedSearchSidebar

## Phase 3: Content (Week 3–4)

Add content management features.

- Build Collections pages (list, detail, create, edit, my-collections)

- Build Articles pages (list, detail)

- Build Forum pages (home, category, thread, create)

- Add Tags page

## Phase 4: Polish (Week 4–5)

Static pages, tools, and refinement.

- Build static pages (About, FAQ, Terms, Vision, Guidelines)

- Build Contact page

- Build AI tool pages (Price Evaluator, BG Removal)

- Expand Admin dashboard (user mgmt, content moderation, system settings)

- End-to-end testing, bug fixes, performance optimization

# 8. Decision Matrix

| Criterion | Option A (Claude) | Option B (Gemini) |
| --- | --- | --- |
| Timeline | 2–4 weeks | 2–3.5 weeks |
| Edge Functions to rewrite | 3 (Gemini → Claude) | 1–2 (adapt send-email, optional verify) |
| Edge Functions dropped | 0 | 3 (extract-content, extract-post, analyze-guitar) |
| Unique assets kept | All (catalog, serial decoder, extraction pipeline, email, KPI) | Most (catalog, serial decoder, email, KPI). Lose extraction pipeline. |
| AI quality (structured extraction) | Higher (Claude excels here) | Lower (Gemini Flash is faster but less precise) |
| AI cost per request | Higher (~$0.003–0.015 per request) | Lower (~$0.001–0.005 per request) |
| Maintenance complexity | Higher (14 Edge Functions, 2 AI providers conceptually) | Lower (8 Edge Functions, 1 AI provider) |
| Future flexibility | Can switch AI per function | Locked to Gemini ecosystem |
| Risk | Medium (rewrites could introduce bugs) | Low (deploy as-is) |

Bottom line: If the 2-phase extraction pipeline and advanced AI capabilities are core to TWNG's value proposition, choose Option A. If speed-to-market and cost efficiency are the priority, choose Option B. Both options result in the same frontend work for the feature gap.