TWNG

Marketing Launch Work Plan

Every Guitar Has a Story

# Executive Summary

TWNG is a platform for guitar collectors and enthusiasts to document, showcase, and share the stories behind their instruments. The platform launches with: Explore, Collections, Tags, Articles, Forum, About pages, plus guitar/collection upload functionality.

Primary Challenge: Building initial critical mass. A platform for showcasing guitars needs viewers to make posting worthwhile. This plan prioritizes audience-building before aggressive user acquisition.

Strategy: Content-first approach. Build audience through valuable guitar content, then convert engaged followers into platform users.

# Current State Assessment

Based on the blueprint framework, TWNG is positioned between Phase 2 (Brand Identity) and Phase 3 (Website). The brand exists but marketing infrastructure is not yet built.

| Phase | Status | Notes |
| --- | --- | --- |
| Phase 1: Idea Validation | Complete | Niche defined: guitar collectors/documentation |
| Phase 2: Brand Identity | Complete | Name, logo, tagline established |
| Phase 3: Website | In Progress | Platform ready in days; marketing pages needed |
| Phase 4: Content Engine | Not Started | Priority focus of this plan |
| Phase 5: Acquisition | Not Started | Will activate after content foundation |
| Phase 6: Onboarding | Not Started | Needed once users start signing up |

# 30-Day Launch Work Plan

## Week 1: Foundation & Pre-Launch

Goal: Prepare all marketing infrastructure before platform goes live.

### 1.1 Website Marketing Pages

- Create compelling About page with founder story (personal guitar stories build authenticity)

- Add value proposition section: why TWNG vs. posting on Instagram or Facebook groups

- Create feature tour/preview showing Collections, Tags, Forum, Articles sections

- Add social proof section (even placeholder: "Join 500+ collectors")

- SEO basics: meta descriptions, OG tags for social sharing

### 1.2 Email Infrastructure

- Set up email provider (recommended: ConvertKit or Loops for creator focus)

- Create welcome email sequence (4-5 emails):

Email 1: Welcome + platform overview

Email 2: Featured guitar story (content sample)

Email 3: How to document your first guitar

Email 4: Community highlights

Email 5: Invitation to join + early member benefits

### 1.3 Social Media Setup

- Instagram: Primary platform (guitar content is highly visual)

- YouTube: Long-form guitar stories and documentation tutorials

- TikTok: Short-form viral guitar content

- Facebook: Community group for guitar collectors

### 1.4 Content Calendar Setup

Generate 30 days of content topics using AI. Categories should include: guitar history, collector spotlights, documentation tips, rare finds, guitar care, brand deep-dives, and community stories.

## Week 2: Content Engine Activation

Goal: Begin building audience before user acquisition push.

### 2.1 Launch Content Production

- Publish 1 article on TWNG Articles section (flagship piece showing platform value)

- Post daily on Instagram (minimum 1 feed post + 3-5 stories)

- Publish 2-3 YouTube Shorts per week

- Cross-post to TikTok

### 2.2 Content Automation Setup

Set up Make.com or Zapier automation: New article published triggers auto-posting to LinkedIn, Twitter/X, and Facebook with AI-generated captions customized per platform.

### 2.3 Seed Content on Platform

- Team uploads 20-30 guitars with complete stories and documentation

- Create 3-5 showcase collections demonstrating platform capabilities

- Start 5-10 forum threads on popular discussion topics

### 2.4 Community Seeding

- Join and participate authentically in: r/guitar, r/guitars, r/guitarcollecting, r/luthier

- Engage in Facebook groups: Vintage Guitar Collectors, brand-specific groups (Gibson, Fender, etc.)

- Participate in forums: The Gear Page, My Les Paul Forum

## Week 3: Soft Launch & First Users

Goal: Get first 50-100 real users on the platform.

### 3.1 Direct Outreach Campaign

- Identify 100 guitar collectors/enthusiasts from Instagram, YouTube, forums

- Personal outreach offering "Founding Member" status with benefits:

Permanent badge on profile

Input on future features

Featured placement when platform grows

- Goal: Convert 50% (50 users) in first week

### 3.2 Influencer/Creator Partnerships

Reach out to 10-15 guitar YouTubers or Instagram accounts (10K-100K followers preferred) offering early access to feature their collections. Provide them content they can share with their audience.

### 3.3 Content Acceleration

- Feature early user collections in content (with permission)

- Create "Guitar of the Week" series highlighting community submissions

- Publish user-generated stories as Articles on the platform

## Week 4: Paid Acquisition Test

Goal: Test paid channels and identify what works.

### 4.1 Meta Ads Test Campaign

Budget: $500-1,000 for initial test

Audience: Interest targeting: Guitar, Fender, Gibson, Vintage instruments, Guitar collection, Music equipment

Creative: 3-4 ad variations:

A) Carousel showing beautiful guitar collections

B) Video: "Your guitars have stories. Tell them."

C) Static image with tagline

D) User-generated content from early members

### 4.2 Google Ads Test

Budget: $300-500 for initial test

Keywords: "guitar collection app", "document guitar collection", "guitar inventory software", "guitar catalog", "organize guitar collection"

### 4.3 Measurement & Iteration

Track: Cost per signup, cost per guitar uploaded, signup to upload rate, 7-day retention. Kill underperforming ads after 3-4 days. Scale winners.

# Content Strategy Deep Dive

## Content Pillars

| Pillar | Description | Content Examples |
| --- | --- | --- |
| Guitar Stories | The emotional, historical narrative behind instruments | "The guitar my grandfather brought from Italy in 1952" |
| Documentation | Practical guides for cataloging collections | "How to photograph your guitar for insurance" |
| Collector Spotlight | Feature community members and their collections | "Inside John's 47-guitar vintage collection" |
| History & Culture | Guitar history, brand stories, famous instruments | "The 5 most expensive guitars ever sold" |
| Tips & Care | Maintenance, storage, valuation advice | "How humidity destroys guitars (and how to prevent it)" |

## Content Calendar: First 30 Days

Below is a sample posting schedule. Adjust based on team capacity.

| Platform | Frequency | Content Type | Time Investment |
| --- | --- | --- | --- |
| Instagram Feed | 1x daily | High-quality guitar photos with stories | 30 min/post |
| Instagram Stories | 3-5x daily | Behind-scenes, polls, Q&A, reposts | 15 min total |
| Instagram Reels | 3x weekly | Short guitar videos, tours, reveals | 1 hour/reel |
| YouTube Shorts | 3x weekly | Repurposed from Reels + original | 20 min/short |
| TikTok | 3x weekly | Cross-posted from Reels/Shorts | 10 min/post |
| TWNG Articles | 1-2x weekly | Long-form guitar stories, guides | 2-3 hours/article |
| Newsletter | 1x weekly | Curated highlights, new features | 1 hour/issue |

# Key Metrics & Success Criteria

## 30-Day Targets

| Metric | Target | Stretch Goal |
| --- | --- | --- |
| Registered Users | 200 | 500 |
| Guitars Documented | 500 | 1,000 |
| Collections Created | 50 | 100 |
| Instagram Followers | 1,000 | 2,500 |
| Email Subscribers | 300 | 500 |
| Forum Posts | 100 | 250 |
| 7-Day Retention Rate | 30% | 40% |

## North Star Metric

Guitars Documented Per Week. This metric captures both acquisition (new users) and engagement (users actually using the platform). A user who signs up but never adds a guitar provides no value to the community.

# Competitive Positioning

TWNG operates in a space with several adjacent competitors. Key differentiation points:

| Competitor | Their Focus | TWNG Differentiation |
| --- | --- | --- |
| Instagram/Facebook | General social media, photos disappear in feed | Dedicated permanent collection, organized catalog |
| Guitar Forums | Discussion-focused, poor media organization | Visual-first, story-centric documentation |
| Reverb/eBay | Buying/selling transactions | Showcase without selling pressure |
| Spreadsheets | Personal inventory only | Community, sharing, discovery |

## Core Messaging

Primary Tagline: "Every Guitar Has a Story"

Supporting Messages:

"Document your collection. Share your passion."

"Finally, a home for your guitars."

"Where collectors become community."

# Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Cold Start Problem | Empty platform discourages new users | Seed with 50+ team-created collections before launch |
| Low Upload Rate | Users sign up but don't add guitars | Simplified onboarding, email nudges, featured placement incentive |
| No Return Visits | One-time users don't build community | Forum activity, notifications, weekly digest emails |
| Content Quality | Low-effort posts dilute platform value | Featured section curates best content, community moderation |
| Paid Acquisition Costs | High CAC makes growth unsustainable | Test small, focus on organic/community channels first |

# Immediate Next Steps (This Week)

- Platform Readiness: Confirm staging.twng.com is fully functional. Test all user flows.

- Seed Content: Team uploads minimum 30 guitars with full stories before any external promotion.

- Social Setup: Create Instagram, TikTok, YouTube accounts. Secure consistent handles.

- Email Setup: Configure email provider and welcome sequence.

- Content Batch: Create first week of content (7 Instagram posts, 3 Reels, 1 article).

- Outreach List: Build list of 100 potential founding members from Instagram, forums, YouTube.

---

TWNG Marketing Launch Plan

Prepared: January 2025